## WBS
WBS Level | WBS ID | Task Name | Status | DMAIC Phase | CRISP-DM Phase | Description
1 | 1 | Business Understanding | 7. Documented & Approved | Define | Business Understanding | Establish the technical, governance, and reproducibility foundation for the Golf Performance Analytics pipeline before any data ingestion or analysis. This phase answers: “What environment, rules, and audit structures will ensure our project remains reproducible and professionally governed?”
2 | 1.1 | Setup & Configuration | 7. Documented & Approved | Define | Business Understanding | This is the **governed environment bootstrapping** step. By initializing logging, validation, and audit tools at the top of the pipeline, every subsequent cell (2.x → 6.x) automatically inherits the same governance rigor. This ensures reproducibility, traceability, and readiness for DMAIC’s **Control** phase — all from the first line of code.
2 | 1.2 | Governance Reporting Utilities (view layer) | 7. Documented & Approved | Define | Business Understanding | Without a view layer, governance is trapped in Python lists and CSV exports. This utility turns those raw logs into something a project sponsor, instructor, or peer reviewer can actually read inside the notebook, at any point in the pipeline. It also standardizes how we review individual phases (2.x, 3.x) without rewriting reporting code.
1 | 2 | Data Understanding | 7. Documented & Approved | Measure | Data Understanding | Establish a governed, analyzable base table from the raw GolfShot vendor export before any cleaning, filtering, or enrichment in Section 3. This phase answers: “What do we actually have, how complete is it, and what problems do we need to control for?”
2 | 2.1 | Load Raw GolfShot Data | 7. Documented & Approved | Measure | Data Understanding | This step formalizes the data hand-off between GolfShot and the analytics pipeline. By introducing row_id immediately, we ensure that every observation downstream — whether in filtered, enriched, or reshaped form — can be traced back to its original vendor row. If GolfShot’s schema changes, this step will fail fast, preventing silent corruption of later transformations.
2 | 2.2 | Standardize Schema & Datatypes | 7. Documented & Approved | Measure | Data Understanding | This is the first step where we define the internal contract for the rest of the notebook. Every subsequent enrichment (holes, facilities, clubs) will assume these names and dtypes. By cleaning percent fields and timestamps here, we avoid inconsistent logic later on.
2 | 2.3 | Initial Data Profiling | 7. Documented & Approved | Measure | Data Understanding | This is the DMAIC “Measure” checkpoint: we need to know the actual data quality before dropping, enriching, or reshaping anything. By freezing a profile here, we can later prove that rows were removed or repaired intentionally and not lost silently.
2 | 2.4 | Core Field Validation & Logical Consistency | 7. Documented & Approved | Measure | Data Understanding | We want to discover bad or suspicious records before the cleaning and enrichment phases. By logging these findings instead of dropping rows now, we preserve auditability and give downstream steps the option to filter or repair.
2 | 2.5 | Initial Vendor Yardage Validation | 7. Documented & Approved | Measure | Data Understanding | Club-distance and dispersion analytics in 3.x depend on trustworthy yardage. By flagging bad yardages here (without dropping them), we give downstream steps a clean, governed way to filter or down-weight low-quality shots while preserving lineage.
2 | 2.6 | Governance Close-Out (Data Understanding) | 7. Documented & Approved | Measure | Data Understanding | This is the control gate between Data Understanding (2.x) and Data Preparation (3.x). By archiving here, we can always roll back or compare later steps to a known-good, validated version.
1 | 3 | Data Preparation | 7. Documented & Approved | Analyze | Data Preparation | Phase 3 transforms raw, inconsistent golf-shot and round data into a governed, analysis-ready data foundation. Across 10+ submodules, it establishes data quality, feature engineering, and governance infrastructure that make the downstream analysis (Phases 4–6) trustworthy, reproducible, and auditable. This phase is the technical backbone of the Golf Performance Analytics Capstone—turning 15 years of round-level data and 5 years of shot-level data into validated, feature-rich datasets aligned with Six Sigma DMAIC and CRISP-DM standards.
2 | 3.1 | Round-level Validity & Features | 7. Documented & Approved | Analyze | Data Preparation | Ensure every round in the dataset represents a complete, valid, and chronologically traceable scoring event. This phase transforms hole-level raw data into a structured, governed round-level dataset.
3 | 3.1.1 | Filter Invalid Hole Records | 7. Documented & Approved | Analyze | Data Preparation | All subsequent preparation and analysis steps rely on authentic scoring data. Rows with zero or missing scores usually indicate incomplete rounds, test entries, or device-sync placeholders. Filtering them here ensures that later KPI and round-completeness logic operate on clean, valid records.
3 | 3.1.2 | Calculate Holes Scored per Round | 7. Documented & Approved | Analyze | Data Preparation | Round completeness is central to scoring analysis. If a round only has 6 or 14 holes logged, we don’t want to treat it the same as a full 9- or 18-hole round. By creating this helper early, later steps (3.1.3–3.1.4) can reliably join to it and keep only complete rounds.
3 | 3.1.3 | Attach Round Hole Counts & Identify Partial Rounds | 7. Documented & Approved | Analyze | Data Preparation | Partial or non-standard rounds can distort round-level KPIs and scoring trends. By flagging them early, we preserve round completeness integrity before filtering in 3.1.4. This ensures that only legitimate 9- or 18-hole rounds are included in scoring and trend analyses.
3 | 3.1.4 | Keep Only Complete Rounds (9 or 18 Holes) | 7. Documented & Approved | Analyze | Data Preparation | Round-level analytics (scoring averages, progression, facility comparisons) are only meaningful when the round is complete. Including partial rounds would artificially lower scores and distort player trends. By locking this rule here, all downstream 3.1.x steps can safely assume “this is a real round.”
3 | 3.1.5 | Assign Sequential Round Numbers per Player | 7. Documented & Approved | Analyze | Data Preparation | Player performance improvement can only be measured relative to the order of play. By assigning a sequential round number, we enable time-series or “career progression” analysis that is resilient to calendar irregularities or data gaps. This forms the basis for “round progression,” moving averages, and skill-trend features in later phases.
3 | 3.1.6 | Assign Sequential Visit Number per Player × Course | 7. Documented & Approved | Analyze | Data Preparation | Players often improve faster on a course the more they play it. By sequencing visits at the (player, facility, course) level, we can separate “overall skill growth” from “I know this course better now,” which leads to better coaching and more accurate performance analytics.
3 | 3.1.7 | Create Round Identifiers & Sequencing | 7. Documented & Approved | Analyze | Data Preparation | Hole-level data is great for shot and putting analysis, but most reporting is done at the round grain. A surrogate round_id gives us a stable join key for round-level aggregates, exports, and dimensional tables — even if the original vendor keys change or we need to re-ingest. The audit-friendly round_key makes it easy to trace a record back to “who played where and when.”
3 | 3.1.8 | Round-level Time Validity & Features | 7. Documented & Approved | Analyze | Data Preparation | Establish temporal context and data quality at the **round level** — ensuring that every round has accurate, interpretable, and analysis-ready time features.
4 | 3.1.8.1 | Derive Time Features | 7. Documented & Approved | Analyze | Data Preparation | Time features allow analysts to connect scoring performance with real-world temporal factors — for example, identifying whether early-morning rounds produce better results, or if weekend rounds are more error-prone due to pace-of-play or fatigue. This step begins building the “temporal dimension” that enables longitudinal and behavioral insight.
4 | 3.1.8.2 | Validate Round Time Quality | 7. Documented & Approved | Analyze | Data Preparation | Timestamps in mobile golf apps can be off due to timezone, sync, or manual-entry quirks. If we don’t flag those out-of-band times, any analysis of “morning vs afternoon” or “weekday vs weekend” can get skewed. By annotating (not deleting) these rows, we preserve scoring data but make it easy to filter on quality later.
4 | 3.1.8.3 | Derive Seasonal & Annual Context | 7. Documented & Approved | Analyze | Data Preparation | This step enables seasonality, progression, and year-over-year comparisons. By structuring play into time-based dimensions, we can: Identify seasonal scoring patterns Detect improvement over multiple years of data Normalize results by season or year in downstream analysis
3 | 3.1.9 | Rename Columns for Analysis | 7. Documented & Approved | Analyze | Data Preparation | Consistent naming conventions make the dataset predictable, easier to join, and safer for reuse in future pipelines. They also prevent subtle errors when combining tables of different grains (round, hole, or shot).
3 | 3.1.10 | Round-level Validity & Features Closeout | 7. Documented & Approved | Analyze | Data Preparation | This step establishes a **formal control point** — verifying completeness, audit trails, and quality prior to enrichment. It represents a **CRISP-DM “Measure → Analyze” handoff** and a **Six Sigma “Define-to-Measure” gate**, ensuring analytical integrity as the dataset advances in grain and complexity.
2 | 3.2 | Hole-Level Validity & Features | 7. Documented & Approved | Analyze | Data Preparation | Normalize and enrich hole-level columns in `golf_valid` so downstream steps (putting flags, GIR/FIR analysis, scoring by par) can rely on consistent `hole_*` fields.
3 | 3.2.1 | Derive Hole-Level Context Features | 7. Documented & Approved | Analyze | Data Preparation | Most golf performance questions at the hole level boil down to “how did we score on par X holes” or “which holes blew up the round?” By standardizing these features here, later sections (putting flags, outcome quality, dispersion) can assume a consistent, labeled hole context without having to recalculate it.
3 | 3.2.2 | Derive Hole-level Putting Flags | 7. Documented & Approved | Analyze | Data Preparation | Putting is one of the largest differentiators in scoring consistency. These standardized flags allow for quick segmentation of putting performance—by GIR vs. non-GIR, over-expected performance, and overall 3-putt frequency—without re-engineering logic in downstream notebooks or dashboards.
3 | 3.2.3 | Derive Hole-level Outcome Quality Signals | 7. Documented & Approved | Analyze | Data Preparation | Beyond raw scores, golf performance improvement depends on understanding how each hole unfolded. This logic introduces structured metrics for recovery performance, opportunity conversion, and avoidable errors—bridging the gap between outcome (score) and process (execution quality)
3 | 3.2.4 | Hole-Level Validity & Features Closeout | 7. Documented & Approved | Analyze | Data Preparation | This step serves as the final **governance and spatial enrichment checkpoint** for hole-level data. In addition to validating all hole-level features and performance metrics, it now introduces **hole-level shot centroids**—the median latitude and longitude of all shots observed for each `(facility, course, hole_number)` combination. These centroids (`hole_lat`, `hole_lon`) establish a stable **geospatial anchor** for hole-level analysis and visualization in later phases, ensuring that every hole can be mapped even if full tee and pin coordinates are unavailable.
2 | 3.3 | Club-level Validity & Features | 7. Documented & Approved | Analyze | Data Preparation | The club-level feature engineering phase (3.3.x) transforms shot-level performance data into strategic, per-club profiles that quantify both distance control and accuracy dispersion. It connects detailed shot geometry to player–club performance insights, producing calibrated dispersion cones and reliability metrics for every club in the bag.
3 | 3.3.1 | Build Player–Club Planning Profile | 7. Documented & Approved | Analyze | Data Preparation | This is the club-level anchor table for the rest of 3.3. Later steps (dispersion, rollups, player-facing summaries) will join back to this profile so we don’t have to recompute yardage statistics. By enforcing a schema gate here and recording the sufficiency rule, we can explain to stakeholders why some player–club pairs don’t have trustworthy distances.
3 | 3.3.2 | Player–Club–Hole Dispersion | 7. Documented & Approved | Analyze | Data Preparation | Distance alone doesn’t tell the full story — a club that goes 150y but sprays 25y left/right isn’t the same as a club that goes 150y and stays within 8y. This step converts raw GPS into operational dispersion metrics that can be rolled up in 3.3.3 and attached back to player_club_profile in 3.3.4. By logging the anchors and the percentile used, the dispersion logic is reproducible and auditable.
3 | 3.3.3 | Player–Club Dispersion Rollup | 7. Documented & Approved | Analyze | Data Preparation | This step converts raw hole-by-hole dispersion into usable, club-level accuracy metrics — essential for understanding which clubs are consistent versus erratic. By weighting results based on the number of shots, this method gives more confidence to dispersion metrics supported by robust data and reduces noise from under-sampled holes. The output serves as the accuracy companion to the distance metrics from 3.3.1 and will be merged in 3.3.4 to create a unified performance profile.
3 | 3.3.4 | Attach Dispersion to Distance Profile | 7. Documented & Approved | Analyze | Data Preparation | This step fuses the distance (power) and dispersion (accuracy) metrics into one master profile, giving each player–club combination a complete performance fingerprint. It’s a key integration point between shot-level precision and strategic planning analytics — bridging accuracy and consistency with realistic on-course club selection expectations. By making this join idempotent and fully governed, the process remains repeatable and traceable for future enrichment phases.
3 | 3.3.5 | Enrich Player–Club Profile with Dispersion Cone Fields | 7. Documented & Approved | Analyze | Data Preparation | Keeps the dispersion logic centralized in the data pipeline (not in Tableau). Guarantees that all clubs for a given player share the same angular model, making cones visually consistent. Uses the best-measured club (1W) as the authority to avoid overfitting to sparse irons/wedges. Makes Phase 4 dashboards simpler: width = “already in the table.”
3 | 3.3.6 | Club-Level Validity & Features Closeout | 7. Documented & Approved | Analyze | Data Preparation | This closeout ensures that the **club-level analysis pipeline is auditable, traceable, and production-ready** before transitioning to visualization or statistical modeling. By freezing the schema and verifying completeness here, Phase 4 (e.g., power-vs-precision mapping or performance vector modeling) can rely on consistent, validated data. It also documents the key business assumption: that player–club metrics are mature enough for higher-level analytics without needing re-engineering in Phase 3.
2 | 3.4 | Facility-level Validity & Features | 7. Documented & Approved | Analyze | Data Preparation | This phase expanded the dataset from individual rounds and clubs to the facility level, consolidating each golf course’s identifying, geographic, and temporal attributes into a unified dimension table (facilities). The goal was to establish each facility’s identity, location, and timezone so that future enrichment and analysis can align all shot-, hole-, and round-level data to the correct geospatial context.
3 | 3.4.1 | Build / Refresh Facilities Table | 7. Documented & Approved | Analyze | Data Preparation | This step creates the single source of truth for all facility-level operations (geocoding, timezone lookup, and GolfCourseAPI enrichment). By merging and preserving editable columns, it enables a reproducible and human-in-the-loop workflow — users can correct or supplement the data without breaking the pipeline. It also logs the assumption that hint_city and hint_state_abbr will be user-supplied when possible, ensuring transparency in future enrichment accuracy.
3 | 3.4.2 | Derive Facility Coordinates from Observed Shots | 7. Documented & Approved | Analyze | Data Preparation | This step creates the first spatial grounding of each course purely from observed data. These provisional centroids are essential for mapping, time zone derivation, and later geocoding/API validation steps. Because the merge is idempotent, analysts can safely rerun this step after upstream changes without corrupting prior edits or cached data.
3 | 3.4.3 | Geocode Facilities Missing Coordinates | 7. Documented & Approved | Analyze | Data Preparation | Accurate geographic coordinates are essential for later time zone alignment, API enrichment, and mapping visualizations. This step ensures every facility–course combination has the best available location data — either empirically from shot data, user hints, or reliable geocoding services — while maintaining a clear audit trail of data provenance (geo_source). The idempotent merge guarantees safe re-runs after users fill in missing hints or correct locations manually.
3 | 3.4.4 | Build Facility Timezones from Coordinates | 7. Documented & Approved | Analyze | Data Preparation | Establishing a timezone for each facility is a critical precursor to all temporal normalization tasks in later phases. It enables accurate conversion of timestamps into local round start times, ensuring that time-of-day, weekday/weekend, and seasonal analyses are consistent across regions. By enforcing defaults and maintaining an audit trail, this step guarantees completeness and reproducibility in temporal data enrichment.
3 | 3.4.5 | Enrich Facilities from GolfCourseAPI (with cache) | 7. Documented & Approved | Analyze | Data Preparation | This is the controlled integration point with the external GolfCourseAPI. It decouples network-dependent enrichment from the core dataset, ensuring that: The pipeline can be safely re-run offline using cached data. Users can manually correct or re-run specific facilities (run_api_again=True). No external API errors or rate limits can corrupt the canonical facilities table. In later steps (3.4.6 – 3.4.9), this cache becomes the trusted source for slope, rating, and location metadata enrichment.
3 | 3.4.6 | Parse and Normalize Cached Facility API Data | 8. Future Enhancement | Analyze | Data Preparation | Parse JSON payloads and normalize for merging.
3 | 3.4.7 | Validate Facility Locations vs Geocoded Data | 8. Future Enhancement | Analyze | Data Preparation | Compare coordinates and flag mismatches.
3 | 3.4.8 | Check GolfCourseAPI Course Data Against USGA | 8. Future Enhancement | Analyze | Data Preparation | Manual verification and note capture.
3 | 3.4.9 | Apply to Facilities Table | 8. Future Enhancement | Analyze | Data Preparation | Apply confirmed data to facilities table.
3 | 3.4.10 | Facility-level Close-Out | 8. Future Enhancement | Analyze | Data Preparation | Close out 3.4 if future enhancements are added.
2 | 3.5 | Phase 3 Close Out | 7. Documented & Approved | Analyze | Data Preparation | Step 3.5 finalizes Phase 3: Data Preparation, transforming the governed, cleaned, and enriched GolfShot dataset into a fully documented, analysis-ready foundation for Phases 4–6. It completes the bridge between data engineering and analytics deployment, ensuring every table, column, and transformation has been validated, logged, and exported with complete traceability.
3 | 3.5.1 | Create DataFrames for Phase 4 | 7. Documented & Approved | Analyze | Data Preparation | Adds a durable hole_id (round_id + "-" + hole_number) to golf_valid so every hole has a unique, reproducible key. Splits the governed master table into three analysis-ready DataFrames: golf_rounds — 1 row per round_id, containing all round-level, player-level, facility-level, and temporal context fields needed for filtering and aggregation. golf_holes — 1 row per scored hole (hole_id), with all hole-level scoring and performance metrics, plus round context for flexible dashboard filtering. golf_shots — 1 row per shot (where shot_club exists), retaining shot-level GPS and yardage diagnostics from Step 2.5, along with its round/hole context for blending and drill-downs. Registers all four tables — golf_valid, golf_rounds, golf_holes, and golf_shots — in the master data dictionary. Each call to generate_data_dictionary() documents table-level metadata, including: table_name each column’s dtype a clear business definition in description the lineage (which 3.x step or source system produced it). This ensures that as Phase 4 begins, every analytical dataset can be traced back to its preparation logic, supporting reproducibility and governance standards.
3 | 3.5.2 | Data Preparation Close-Out (Exports) | 7. Documented & Approved | Analyze | Data Preparation | This step officially closes Phase 3: Data Preparation, consolidating all validated data, metadata, and governance artifacts into final export formats. It functions as the handoff point between data engineering and analysis, ensuring that all deliverables are complete, reproducible, and ready for Tableau, Power BI, or Python-based modeling in Phase 4.
1 | 4 | Modeling & Visualization | 7. Documented & Approved | Improve | Modeling | Generate analytical insights and visualizations.
2 | 4.1 | Diagnostic Performance Analysis using all relevant KPIs developed in data preparation | 7. Documented & Approved | Improve | Modeling | Dashboard in Tableau to evaluate scoring trends and trouble patterns. Scoring by type (eagle, birdie, etc.),scrambling, putting, other metrics we created in etc. all filterable by person, facility, course, round, time features, etc.
2 | 4.2 | Shot-level Modeling (to execute my on-course strategy) | 7. Documented & Approved | Improve | Modeling | Create a vector for misses to visualize. Using data from 3.3.3, make a triangle, using the most statistically significant of your data (Driver) as the end dispersion, locate it at and drawing back to your location for all planned distances in player_club_profile except wedges <100 yards.
2 | 4.3 | Case Study: Lewisburg Elks Hole 9 | 7. Documented & Approved | Improve | Modeling | Facility-level context, Round-level context, Hole-level context from dashboard in 4.1 , Shot-level (mistakes with driver on 9) from 4.2. Produce visual story of dispersion and miss tendencies.
1 | 5 | Evaluation | 7. Documented & Approved | Control | Evaluation | Interpret analytical results and identify improvement levers.
2 | 5.1 | Summarize Key Findings & Hypotheses | 7. Documented & Approved | Control | Evaluation | Interpret analysis outcomes vs hypotheses.
2 | 5.2 | Quantify Improvement Opportunities | 7. Documented & Approved | Control | Evaluation | Identify practice targets and measurable improvements.
2 | 5.3 | Document Lessons Learned | 7. Documented & Approved | Control | Evaluation | Record key assumptions and insights for reuse. Also identify useful metrics to track in the future due to current data limitations.
1 | 6 | Deployment | 7. Documented & Approved | Control | Deployment | Package outputs, document governance, and sustain the process.
2 | 6.1 | Generate Final Data Dictionary | 7. Documented & Approved | Control | Deployment | Compile metadata and field definitions for final datasets.
2 | 6.2 | Export Artifacts | 7. Documented & Approved | Control | Deployment | Export datasets, logs, dictionaries, and documentation.
2 | 6.3 | Summarize Control Plan | 7. Documented & Approved | Control | Deployment | Outline how to re-run, validate, and sustain improvements.

## Status
Status | Description / Intent
1. Planned / Scheduled | Defined scope, not yet started. Requirements clear, waiting for start.
2. In Progress | Currently being developed, tested, or validated.
3. Cancelled / Superseded | Work formally discontinued or replaced by another method.
4. On Hold | Temporarily paused (waiting on data, dependency, or resource).
5. Completed (Pending Review) | Code or logic finished; awaiting peer or governance review.
6. Under Review / Quality Gate | Step undergoing validation, testing, or stakeholder sign-off.
7. Documented & Approved | Governance logs, data dictionary, and documentation finalized.
8. Future Enhancement | Steps designated for future enhancements.

## Org
DMAIC | CRISP-DM
Define | Business Understanding
Measure | Data Understanding
Analyze | Data Preparation
Improve | Modeling
Control | Evaluation
Control | Deployment

## Denormalization Decision
<class 'pandas.core.frame.DataFrame'>
RangeIndex: 3987 entries, 0 to 3986
Data columns (total 61 columns):
# Column Non-Null Count Dtype | golf_rounds | golf_holes | golf_shots
0 player_name 3987 non-null string | YES | YES | YES
1 round_dt 3987 non-null datetime64[ns] | YES | YES | YES
2 facility 3987 non-null string | YES | YES | YES
3 course 3987 non-null string | YES | YES | YES
4 round_score 3987 non-null Int64 | YES | ADD | ADD
5 round_fairway_strokes 3987 non-null Int64 | YES | ADD | ADD
6 round_putts 3987 non-null Int64 | YES | ADD | ADD
7 round_gir 3987 non-null float64 | YES | ADD | ADD
8 hole_number 3987 non-null Int64 | NO | YES | YES
9 hole_par 3987 non-null Int64 | NO | YES | ADD
10 shot_fairway_hit_type 3987 non-null string | NO | YES | YES
11 hole_fairway_strokes 3987 non-null Int64 | NO | YES | ADD
12 hole_putts 3987 non-null Int64 | NO | YES | ADD
13 hole_score 3987 non-null Int64 | NO | YES | ADD
14 hole_gir 3987 non-null boolean | NO | YES | ADD
15 shot_club 1946 non-null string | NO | NO | YES
16 shot_direction 1946 non-null string | NO | NO | YES
17 shot_start_lat 1946 non-null Float64 | NO | NO | YES
18 shot_start_lon 1946 non-null Float64 | NO | NO | YES
19 shot_end_lat 1946 non-null Float64 | NO | NO | YES
20 shot_end_lon 1946 non-null Float64 | NO | NO | YES
21 yardage 1946 non-null Float64 | NO | NO | YES
22 yardage_to_pin 759 non-null Float64 | NO | NO | YES
23 row_id 3987 non-null int64 | NO | NO | YES
24 yardage_calc 1946 non-null float64 | NO | NO | YES
25 yardage_error 1946 non-null Float64 | NO | NO | YES
26 yardage_error_abs 1946 non-null Float64 | NO | NO | YES
27 yardage_error_pct 1938 non-null Float64 | NO | NO | YES
28 yardage_suspect 1946 non-null boolean | NO | NO | YES
29 round_holes_scored 3987 non-null Int64 | YES | ADD | ADD
30 round_is_partial 3987 non-null boolean | YES | NO | NO
31 round_no_player 3987 non-null Int64 | YES | ADD | ADD
32 round_no_player_course 3987 non-null Int64 | YES | ADD | ADD
33 round_id 3987 non-null int64 | YES | YES | YES
34 round_key 3987 non-null object | YES | YES | NO
35 date 3987 non-null string | YES | YES | YES
36 time 3987 non-null string | YES | NO | NO
37 hour 3987 non-null Int64 | YES | NO | NO
38 dow 3987 non-null string | YES | ADD | ADD
39 is_weekend 3987 non-null bool | YES | ADD | ADD
40 part_of_day 3987 non-null string | YES | ADD | YES
41 round_time_valid 3987 non-null boolean | YES | NO | NO
42 year 3987 non-null Int64 | YES | ADD | ADD
43 month 3987 non-null Int64 | YES | ADD | ADD
44 month_name 3987 non-null string | YES | ADD | ADD
45 year_month 3987 non-null string | YES | YES | YES
46 season 3987 non-null string | YES | YES | YES
47 round_year_index 3987 non-null Int64 | YES | NO | NO
48 hole_par_bucket 3987 non-null string | NO | YES | ADD
49 hole_strokes_over_par 3987 non-null Int64 | NO | YES | ADD
50 hole_score_name 3987 non-null string | NO | YES | ADD
51 hole_putts_over_expected 3987 non-null Int64 | NO | YES | ADD
52 hole_putts_3plus 3987 non-null boolean | NO | YES | ADD
53 hole_gir_putts_3plus 3987 non-null boolean | NO | YES | ADD
54 hole_notgir_putts_3plus 3987 non-null boolean | NO | YES | ADD
55 hole_scramble_opportunity 3987 non-null boolean | NO | YES | ADD
56 hole_scramble_success 3987 non-null boolean | NO | YES | ADD
57 hole_gir_wasted 3987 non-null boolean | NO | YES | ADD
58 hole_notgir_chip_in 3987 non-null boolean | NO | YES | ADD
59 hole_is_scoring_chance 3987 non-null boolean | NO | YES | ADD
60 hole_is_recovery 3987 non-null boolean | NO | YES | ADD

## Clubs (hidden)
🏌️‍♂️ Golf Clubs in Dataset
Shot Club | Club Name | First Used | Last Used | Min | Max | Mean
1W | Titleist TS2 Driver | 2021-09-11
3W | Titleist TS2 3 Wood | 2021-09-11
3Hy | Titleist TS3 Hybrid 19 Degree | 2021-09-11
4i | Titleist T100 4i | 2021-09-11
5i | Titleist T100 5i | 2021-09-11
6i | Titleist T100 6i | 2021-09-11
7i | Titleist T100 7i | 2021-09-11
8i | Titleist T100 8i | 2021-09-11
9i | Titleist T100 9i | 2021-09-11
Pw | Titleist T100 Pw | 2021-09-11
Gw | Titleist Vokey SM8 50 Degree | 2021-09-11
Sw | Titleist Vokey SM8 54 Degree | 2021-09-11
Lw | Titleist Vokey SM8 58 Wedge | 2021-09-11
1W | Titleist 983K Driver |  | 2021-09-05
3W | Titleist 975F 3 Wood |  | 2021-09-05
3Hy | Titleist 585.H Hybrid 21 Degree |  | 2021-09-05
3i | Titleist 735.CM Chrome 3i |  | 2021-09-05
4i | Titleist 735.CM Chrome 4i |  | 2021-09-05
5i | Titleist 735.CM Chrome 5i |  | 2021-09-05
6i | Titleist 735.CM Chrome 6i |  | 2021-09-05
7i | Titleist 735.CM Chrome 7i |  | 2021-09-05
8i | Titleist 735.CM Chrome 8i |  | 2021-09-05
9i | Titleist 735.CM Chrome 9i |  | 2021-09-05
Pw | Titleist 735.CM Chrome Pw |  | 2021-09-05
Gw | Titleist Vokey Design Spin Milled C-C 52 Degree |  | 2021-09-05
Sw | Titleist Vokey Design Spin Milled C-C 56 Degree |  | 2021-09-05
Lw | Titleist Vokey Spin Milled Oil Can 60 Degree |  | 2021-09-05

## OLD WBS (hidden)
WBS | Title | Status | Description
Python Notebook: Header
0 | Header | Under review | This notebook implements the analytical workflow for the Golf Performance Analytics Capstone, applying the Six Sigma DMAIC framework to over 15 years of GolfShot (golfshot.com) performance data.
It integrates personal shot-level data with the Golf Course API to generate reproducible, geospatial insights into consistency, distance, and accuracy.
Python Notebook: 1. Setup & Configuration
1 | Setup & Configuration | Completed | Initialize the controlled analysis environment for the Golf Performance Analytics project.
Python Notebook: 2. Data Import & Cleaning
2.1 | Load Raw GolfShot Data | Completed | Load the full GolfShot export (15+ years of personal shot- and hole-level performance data) into memory for initial validation and profiling.
2.2 | Standardize & Clean Schema | Completed | Convert the raw vendor export (golf_raw) into a consistent, analysis-ready working DataFrame called golf.
2.3 | Snapshot Clean Data (Private Export) | Completed | Export the cleaned working DataFrame (golf) to a governed local snapshot for audit and traceability.
2.4 | Filter Invalid Hole Records | Completed | Remove rows that do not represent real scoring events and quantify data retention.
2.5 | Calculate Holes Scored Per Round | Completed | Determine how many unique holes were actually scored in each recorded round.
2.6 | Attach Round Hole Counts and Identify Partial Rounds | Completed | Merge each round’s hole count back onto every scored row, and surface partial rounds for review.
2.7 | Keep Only Complete Rounds (9 or 18 Holes) | Completed | Filter the dataset to retain only full, valid rounds—those with exactly 9 or 18 distinct holes played.
2.8 | Assign Sequential Round Numbers per Player | Completed | Assign a chronological round number to each player to establish a consistent sequencing of rounds played over time.
2.9 | Assign Sequential Visit Number per Player × Course | Completed | For each (player_name, facility, course) combination, assign a chronological visit number that indicates how many times that specific player has played that specific course.
2.1 | Export Analysis-Ready Data | Under review | Export governed analysis datasets for downstream use (BI tools, storytelling, dashboards).
Python Notebook: 3. Feature Engineering & Enrichment
3.1 | Derive Time Features | Under review | Add human-readable time context to each round.
3.2 | Validate Round Time Quality | Under review | Evaluate the reliability of recorded tee times and prevent suspicious timestamps from biasing time-of-day analysis.
| Build Course Data Table Using GolfCourseAPI | Not started | Build a per-facility table with all metrics from Golfcourseapi based on the facility and course info in my dataset, store and export
| Check Course Data Against Official USGA | Not started | This is a manual step, as we do not want to violate … USGA … terms and conditions …
| Initialize Geocoding Environment to Test Whether GolfCourse API geocoded data is accurate | Not started | Initialize geocoding environment for facility coordinate resolution? I don’t want to use the HINTS library anymore. I want this to be repeatable for other users, so I think we start with golfcourseapi first, then we pause to check the information manually at USGA, then we set up the environment to test the geocoded info based upon shot-level data.
|  | Not started | Derive per-facility coordinates from recorded shot GPS data (no geocoding yet)
|  | Not started | Compare shot positions to facility centroids (e.g., distance > 10 km) from golfcourseapi
|  | Delete | OLD WAY: Load cached facility coordinates (if available) and identify which facilities still need geocoding
|  | Delete | OLD WAY: Geocode facilities that are still missing coordinates, using Nominatim first and ArcGIS as fallback
|  | Delete | OLD WAY: Combine all coordinate sources, prefer shot-derived results, and update the facility cache
|  | Not started | Should we attach facility latitude/longitude to each round/shot record to create a geo-enriched dataset. Did this before. Not sure the best method yet.
Python Notebook: Handle Shot Distance Outliers
| Check vendor ‘yardage’ column | Completed | Verify shot distances in `yardage` column using latitude/longitude
| Flag shot outliers | Not started | Develop methodology to clean shot data by club based on the table based on template created. Include `player_name` in table so others can reproduce for themselves. Consider adding this as an XLSX helper file in data/processed that users can update based upon their own information. Or create workflow in Python that a user can enter all their information, using my data as examples. “Select the clubs in your bag”, “Enter your club names”, “Enter the minimum and maximum yardage range for each club to remove outliers”, etc.
Python Notebook: KPIs
|  | Not started | Create handicap metrics by course based on golfcourseapi data
|  | Not started | Stokes Gained (would need pro averages)
|  | Not started | Fairways (hit, left, right, short, long…)
|  | Not started | Calculate FIR% (fairways in regulation)
|  | Not started | Calculate GIR% (greens in regulation) and check this against ‘round_gir` column to verify correctness
|  | Not started | Recovery (scramble, sand shot)
|  | Not started | Putting by hole and GIR
|  | Not started | Scoring averages by par type (3, 4, 5)
|  | Not started | Scoring averages by type (eagle, birdie, par, bogey…)
Python Notebook: Visualization Setup
|  | Not started | KPI Dashboard
|  | Not started | Shot dispersion by club
|  | Not started | Visualize facilities and rounds on a map (Folium/Kepler) using the coordinates from golfcourseapi vs. resolved coordinates to gauge differences and make decisions on best one to use. Might need to loop back to those steps after this. Should we move this step up to our geocoding section?
|  | Not started | Identify other trends worth visualizing (e.g., distance gains, scoring consistency, improvement [or lack of] over time).
|  | Not started | Is there a way to create a flyover or a shot tracer of a sliced shot arc? I frequently slice my drive on hole 2 at Lewisburg Elks golf course and want to present a visualization of it.
|  | Not started | Course mapping. Open to all ideas
|  | Not started | Prototype a simple visualization: a score trend chart or a heatmap of missed shots.
|  | Not started | Anything else?
Python Notebook: Quality Checks
|  | Not started | Anything missing?
Python Notebook: Document all Transforms in a Change Log
|  | Not started | Do we use this from notebook? Or is this another product we need to build into each step?
log_step() → standardized pipeline logging
Create and Save a final Data Dictionary
|  | Not started | Do we use this from notebook? Or is this another product we need to build into each step?
validate_columns() → schema validation and enforcement
Export Analysis-ready Tables
|  | Not started | We’ve exported a lot of tables already. Any others worth creating. Any analysis-ready dataframes we missed?
Create Presentation
Not started
Create Presentable README for GitHub (maybe with KPI Dashboard pic)
Not started